## Sheet1
Change Control
Change ID | Date Submitted | Submitted By | Description of Change | Reason | Impact Analysis | Priority | Approval Status | Approved By Date
1 | 2026-07-01 | Exam Department | Forget Password Feature Add | Student use forget password feature | Core Feature, Database Use, minor change in UI,1 Day extra for devleopment | High | Approved | Project Manager 02-july-2026
2 | 2026-07-02 | Finanace Department | Add Feature to pay fee through JazzCash and Easypaisa | Students may not have bank accounts | Database Use, Core Feature and change in UI | High | Approved | Project Manager 03-july-2026
3 | 2026-07-03 | Exam Department | Change button of Download for exam slip | Exam Slip download button not visible | Change in UI | Medium | Pending | ___
4 | 2026-07-04 | Exam Department | Add download button in exam result | Student may download their results | Change in UI | Medium | Pending | ____
5 | 2026-07-05 | Facilitation Center | Make simple buttons in UI for registration | Buttons are not visible properly and interface is complex | Change in UI, Core Feature | HIgh | Approved | Project Manager 06-july-2026